NGO CONNECT

Marketing & Communication Center

Architecture & Phased Delivery Plan (BRD)

| Field | Value |
| --- | --- |
| Document Type | Business Requirements & Architecture Document (BRD) |
| Module | Communication Center (extends Module 11 — Notification & Communication Engine) |
| Version | 1.0 — Draft, Pending Approval |
| Prepared For | Gaurav Shukla, Project Manager, NGO Connect |
| Date | 23 July 2026 |
| Status | Planning — no code or schema changes yet |

# 1. Executive Summary

This document scopes the Marketing & Communication Center requested for the Super Admin Dashboard — a centralized system to reach users via Push, Email, and SMS, with scheduling, segmentation, templates, analytics, and campaign history. It is the natural growth of Module 11 (Notification & Communication Engine), already on the NGO Connect roadmap, expanding from transactional notifications into a full marketing automation platform.

The full requested feature set — multi-channel send, scheduling, 16 audience-segmentation options, templates, A/B testing, click heatmaps, a message-queue operations console, maker-checker approval, and forward compatibility with WhatsApp, AI copywriting, and CRM integration — is realistically 10–13 developer-weeks of work delivered in four phases, not a single release. This document lays out why, and what each phase contains.

Two scope decisions are already locked in for Phase 1, confirmed 23 July 2026:

- SMS is deferred out of Phase 1. Fast2SMS — the SMS provider already integrated in this codebase — is wired to its test-only “Quick” route. Sending real promotional SMS in India requires DLT (Distributed Ledger Technology) registration with a telecom operator — an external, non-code compliance step with its own lead time. Phase 1 ships Push + Email only; SMS is added as soon as DLT registration clears.

- AWS SES is confirmed in production access (not sandbox), so Email campaigns can go out to real, unverified addresses from Phase 1 onward without an AWS approval wait.

WhatsApp is confirmed as a planned future-stage channel (Phase 4) — not merely a hypothetical — and the Phase 1 schema is deliberately designed so it slots in later without a rewrite (see Section 11).

# 2. Business Objectives

The Communication Center exists to drive measurable engagement outcomes, not just to send messages. Every feature in this document should be traceable to one of the following:

- Increase Daily Active Users (DAU)

- Win back inactive users (reduce churn — see callout below)

- Promote new features and app updates

- Announce campaigns, festival wishes, and platform achievements

- Promote NGOs and volunteer opportunities

- Encourage donations

- Increase overall user retention

# 3. Current State Assessment

Before scoping new work, the existing NGOConnectAPI codebase was reviewed directly (not assumed) to establish what is already reusable and what is genuinely missing.

## 3.1 Already Built — Reusable As-Is

| Capability | Found In Codebase | Notes |
| --- | --- | --- |
| Push notifications | FCMService.cs, IFCMService | Firebase Cloud Messaging, singleton service, already handles stale-token cleanup |
| Email sending | AwsSesEmailService.cs, SmtpEmailService.cs, IEmailService | AWS SES confirmed in production access; SMTP fallback also present |
| SMS sending | Fast2SmsService.cs, ISmsService | Wired to test-only “Quick” route — see gap below |
| Per-user notifications | Notifications table (BIGINT PK) | Built for transactional single-user notices (application approved, etc.) — not for bulk campaigns |
| Config management | Settings + SettingsCache | New provider keys/rate limits belong here, not appsettings.json |
| Category/enum values | LookupTypes + LookupValues | Campaign Type, Priority, Status, Channel should all be new LookupValues, not hardcoded enums |

## 3.2 Gaps — Must Be Built Before Phase 1 Can Ship

- No background job engine exists anywhere in the codebase. Hangfire is listed as Module Build Order step 14 in the architecture skill, but no Hangfire, IHostedService, or recurring-job code was found. Every scheduling, queueing, batching, and retry requirement in this spec depends on an async worker outside the request/response cycle — this is Phase 0, foundational, not a Communication Center detail.

- No user communication-preference / opt-out table exists. The spec explicitly requires respecting user preferences before sending promotional messages — this must exist before Campaign v1 ships, not retrofitted after, since providers (SES, FCM) penalize or blacklist senders with high complaint/opt-out-violation rates.

- Fast2SMS is on the test-only “Quick” route (confirmed via code comment in Fast2SmsService.cs). DLT registration is required before any real promotional SMS can be sent — addressed by deferring SMS to a later phase (Section 2).

- Two entries in the architecture skill's confirmed stack no longer match reality and should be corrected once this plan is approved: SMS is documented as “Twilio or MSG91” but the real implementation is Fast2SMS; Cloud is documented as “Azure primary, AWS secondary” but everything actually running (S3 storage, SES email) is AWS-only.

- Real-time “Estimated Recipients” counts, computed live against up to 16 audience-filter combinations at millions-of-users scale, is a query-performance problem in its own right. A naive COUNT() per wizard interaction would violate the platform's own Core Mandate (no COUNT() on hot read paths) — addressed in Section 11 via a cached/pre-aggregated approach.

# 4. Scope Decisions (Confirmed 23 July 2026)

| Decision | Outcome |
| --- | --- |
| Delivery approach | Phased delivery across four phases (this document). Full spec built as a single release was explicitly rejected as too onerous / high-risk for one delivery. |
| SMS in Phase 1 | Excluded. Push + Email only until Fast2SMS DLT registration is complete. SMS becomes a Phase 1.x addition once registration clears — no architecture change needed, just enabling the existing channel. |
| Email provider readiness | AWS SES confirmed in production access — no sandbox/approval blocker for Phase 1 email sends. |
| WhatsApp | Confirmed for a later stage (Phase 4), not merely speculative. Schema designed now so it adds cleanly later (Section 11). |

# 5. Phased Delivery Roadmap

| Phase | Focus | Est. Effort |
| --- | --- | --- |
| Phase 0 — Foundation | Hangfire background job engine; UserCommunicationPreferences table + opt-out enforcement; new LookupValues for Channel/CampaignType/Priority/Status | 1.5–2 dev-weeks |
| Phase 1 — MVP Campaigns | Push + Email only. Campaign wizard (details, channels, core audiences, compose, send-now/one-time-schedule, confirm). Campaign History. Core Dashboard. Test Send. | 3–4 dev-weeks |
| Phase 2 — Targeting, Templates, Recurring | Remaining audience filters (location/gender/age/language/interest/CSV/manual search). Templates module. Recurring schedules + cron. Reusable Segment Builder. Richer analytics charts. | 3 dev-weeks |
| Phase 3 — Operational Maturity | Message Queue console (queued/processing/retry/pause/resume/cancel). A/B testing. Maker-Checker approval workflow. Full audit trail UI. Draft auto-save. Duplicate-send protection. | 3–4 dev-weeks |
| Phase 4 — Confirmed Future Scope | WhatsApp (confirmed for later stage), in-app message center, web push, drip/event-triggered automation, AI-assisted copywriting, send-time optimization, geo-fencing, budget tracking, CRM integration. | Not yet estimated |

Total through Phase 3: approximately 10–13 developer-weeks, assuming one to two developers. This is the number to use in budget and timeline conversations — not the full original feature list treated as a single deliverable.

# 6. Phase 0 — Foundation

Nothing in Phase 1 can be reliably delivered without this phase; it is infrastructure, not user-facing feature work.

### 6.1 Background Job Engine

Integrate Hangfire (already the architecture skill's intended choice for background jobs) against the existing MySQL database. Provides: scheduled one-time jobs (Send Later), recurring jobs (cron-style, for Phase 2 recurring campaigns), automatic retry with backoff, and a dashboard for job visibility — which doubles as a starting point for the Phase 3 Message Queue console.

### 6.2 Communication Preferences

New UserCommunicationPreferences table (one row per user): ReceivePushNotifications, ReceivePromotionalEmails, ReceivePromotionalSms, ReceiveNgoUpdates, ReceiveDonationAlerts, ReceiveVolunteerOpportunities — all boolean, default opt-in for non-promotional categories per the spec's own transactional-bypass rule (OTP, password reset, and critical account alerts always bypass these preferences).

### 6.3 New Lookup Values

Following the platform's LookupTypes/LookupValues pattern (no hardcoded enums): CAMPAIGN_TYPE (Promotion, Announcement, Reminder, Feature Launch, Donation, Volunteer, Emergency, Festival, Survey, Custom), CAMPAIGN_PRIORITY (Low, Normal, High, Critical), CAMPAIGN_STATUS (Draft, Scheduled, Running, Completed, Cancelled, Failed, Paused), CAMPAIGN_CHANNEL (Push, Email, SMS, and later WhatsApp — adding a value, not a code change).

# 7. Phase 1 — MVP Campaigns (Push + Email)

The smallest slice that is genuinely useful and demoable: a Super Admin can create a campaign, pick an audience, compose Push and/or Email content, send immediately or schedule once, and see what happened afterward.

## 7.1 Dashboard (reduced for Phase 1)

Cards: Total Push Sent, Total Emails Sent, Delivery Rate, Open Rate, Click Rate, Failed Messages, Active Campaigns, Scheduled Campaigns, Draft Campaigns. (SMS card and Pie Chart's SMS slice return once SMS is enabled.) Charts: Messages Sent (Daily/Weekly/Monthly toggle), Channel split pie chart (Push vs Email), Recent Campaigns list, Failed Campaigns list.

## 7.2 Create Campaign Wizard

### Step 1 — Campaign Details

- Campaign Name, Internal Notes (never shown to users)

- Campaign Type (dropdown, from CAMPAIGN_TYPE lookup)

- Priority (Low / Normal / High / Critical)

### Step 2 — Communication Channels

- Checkboxes: Push Notification, Email (SMS checkbox visible but disabled with a “coming soon — pending SMS registration” tooltip, so the UI doesn't need rework when SMS activates)

### Step 3 — Audience Selection (Phase 1 subset)

Full audience segmentation (16 options) is significant scope on its own — Phase 1 ships the options that cover the stated goals (DAU, reactivation, feature/NGO/opportunity promotion) without needing new external data (CSV upload, geo radius, interest tagging):

- All Users

- Active Users (opened app within last 7 / 15 / 30 days)

- Inactive Users (not opened for 30 / 60 / 90 days) — the direct anti-churn segment

- New Users (joined Today / 7 Days / 30 Days)

- Users by Organization (select one or multiple NGOs)

- By Role: Volunteers, NGO Admins, Founders, Donors

Deferred to Phase 2: Location (country/state/city/radius), Gender, Age Group, Language, Interest-based, Custom List (CSV upload / paste), Manual user search-and-select — these need either new data collection, geocoding, or heavier UI (CSV parsing, user search) that don't block the MVP's core use cases.

Estimated Recipients count is shown in real time using a cached, pre-aggregated count per segment (refreshed periodically, not computed live per keystroke) — protects the platform's Core Mandate around avoiding expensive queries on hot paths even as user counts scale into the millions.

### Step 4 — Compose Message

Push Notification: Title, Body, Large Image, Deep Link / Landing Screen (Opportunity Details, NGO Profile, Donation Page, Home, Custom URL), Action Button (Donate Now / Apply / Open App / Learn More), Android + iPhone preview.

Email: Rich HTML editor (images, buttons, links), personalization variables ({{UserName}}, {{NGOName}}, {{Opportunity}}, {{DonationAmount}}), attachments (PDF, images), Desktop + Mobile preview.

### Step 5 — Scheduling (reduced for Phase 1)

- Send Now

- Schedule (one-time: date, time, timezone)

Recurring scheduling (Daily/Weekly/Monthly/Yearly/Custom Cron) is Phase 2 — it depends on Hangfire recurring jobs being exercised and proven first with simple one-time schedules.

### Step 6 — Confirmation

Summary screen: audience, channels, estimated recipients, schedule. Explicit confirmation required before sending — no silent auto-send.

## 7.3 Campaign History

Table: Campaign Name, Created By, Created On, Status, Recipients, Delivered, Opened, Clicked, Failed, Channel. Actions: View, Duplicate, Pause, Resume, Cancel, Export. Searchable, filterable, sortable per the UI/UX requirements.

## 7.4 Test Send

Before any real send, allow sending Push/Email to the admin's own account or a short list of selected internal testers — a required guardrail before enabling the wizard's final send button.

# 8. Phase 2 — Targeting, Templates, Recurring

- Remaining audience filters: Location (country/state/city/radius), Gender, Age Group, Language, Interest-based (Education, Environment, Health, Animals, Food, Blood Donation, Disaster Relief, Women Empowerment, etc.), Custom List (CSV upload with Name/Email/Phone, or paste), Manual user search-and-select

- Campaign Templates: save reusable Title/Subject/Message/Images/CTA/Variables by category (Welcome, Donation, Volunteer, Festival, Awareness, NGO Promotion, App Update, Emergency, Custom)

- Recurring schedules (Daily/Weekly/Monthly/Yearly/Custom Cron) via Phase 0's Hangfire recurring jobs

- Reusable Audience Segment Builder — save a filter combination once (e.g. “Donors from Bangalore”, “Animal Welfare Volunteers”), reuse across future campaigns without rebuilding it

- Richer analytics: delivery timeline, open timeline, click charts per campaign

# 9. Phase 3 — Operational Maturity

- Message Queue console: queued / processing / sent / failed counts, retry, priority, worker/queue-size visibility, processing time — built on top of the Hangfire dashboard from Phase 0

- Queue controls: Retry Failed, Pause Queue, Resume Queue, Cancel Queue

- A/B Testing: two message versions, compare open/click/conversion, auto-promote the winner

- Duplicate-send protection: warn admin before accidentally re-sending an identical campaign

- Draft auto-save (every few seconds while composing)

- Campaign clone (duplicate a previous campaign as a starting point)

- Maker-Checker approval workflow (optional, configurable): a campaign creator drafts, a separate Super Admin approves before send

- Full audit log UI surfacing: created by, updated by, sent by, approval history, IP address, timestamp, before/after values — the data itself is captured from Phase 1 onward via the platform's existing AuditLogs table; Phase 3 adds the review screen

# 10. Phase 4 — Confirmed Future Scope

These are not built now, but Phase 1–3's architecture is deliberately shaped so none of them require a schema rewrite:

- WhatsApp campaigns — confirmed for a later stage. Adds cleanly as a new CAMPAIGN_CHANNEL lookup value plus one new provider integration (e.g. WhatsApp Business API) behind the same channel-compose pattern used for Push/Email/SMS.

- In-app message center

- Browser/web push notifications

- Automated drip campaigns and event-triggered notifications (registration, donation, volunteer application)

- AI-assisted message generation and subject-line optimization

- Send-time optimization based on user activity patterns

- Multi-language campaigns with automatic language selection

- Geo-fenced campaigns

- Campaign budgeting and cost tracking

- Integration with CRM / marketing automation platforms

# 11. Database Design (Phase 0 + Phase 1)

Follows existing NGO Connect conventions throughout: soft delete (IsDeleted/DeletedAt/DeletedBy) on every master table, standard audit columns (CreatedAt/CreatedBy/UpdatedAt), category columns via LookupTypes/LookupValues rather than hardcoded values, and BIGINT UNSIGNED primary keys on the one high-volume append table (CampaignRecipients) per the platform's existing rule for tables expected to reach billions of rows.

| Table | Purpose | Key Columns |
| --- | --- | --- |
| Campaigns | One row per campaign | CampaignId (PK), CampaignName, InternalNotes, CampaignTypeLkpId, PriorityLkpId, StatusLkpId, ScheduleType, ScheduledAt, TimezoneId, CreatedBy |
| CampaignChannels | One row per channel selected for a campaign | CampaignId (FK), ChannelLkpId, Title/Body/ImageUrl/DeepLink (Push) or Subject/HtmlBody (Email) — nullable per-channel fields, extensible for SMS/WhatsApp later |
| CampaignAudienceRules | The audience filter combination for a campaign | CampaignId (FK), RuleType, RuleValueJson — JSON storage means new filter types (Phase 2) never require a schema change |
| CampaignRecipients | One row per user per campaign — the largest table | CampaignRecipientId (BIGINT PK), CampaignId, UserId, ChannelLkpId, QueueStatus, ProviderMessageId, SentAt, DeliveredAt, OpenedAt, ClickedAt, FailReason |
| CampaignQueueJobs | Batch/retry tracking for the Hangfire-driven send process | CampaignQueueJobId (BIGINT PK), CampaignId, BatchNumber, Status, RetryCount, NextRetryAt |
| UserCommunicationPreferences | One row per user, opt-in/opt-out flags | UserId (FK), ReceivePushNotifications, ReceivePromotionalEmails, ReceivePromotionalSms, ReceiveNgoUpdates, ReceiveDonationAlerts, ReceiveVolunteerOpportunities |

Phase 2 adds CampaignTemplates and AudienceSegments (saved, reusable filter sets) as siblings to the tables above — no changes to the Phase 1 tables are anticipated.

# 12. Stored Procedure, DAL & API Design

## 12.1 Stored Procedure Pattern

Follows the platform's existing WRITE / LIST / GET / DYNAMIC conventions exactly — no new SP pattern is introduced:

- Campaign_Create, Campaign_Update, Campaign_Cancel — WRITE pattern (returns IsSuccess/Message/CampaignId)

- Campaign_GetList, Campaign_GetById — Dynamic pattern (dashboard/history columns will change every sprint, exactly the scenario the platform's own Typed-vs-Dynamic decision table calls for DynamicRow)

- Campaign_EstimateAudience — its own Dynamic SP, backed by a cached/pre-aggregated count rather than a live join, to protect the Core Mandate's “no COUNT() on hot paths” rule at scale

- CampaignRecipient_MarkDelivered / MarkOpened / MarkClicked / MarkFailed — WRITE pattern, invoked by provider webhooks (SES event notifications, FCM delivery receipts)

## 12.2 DAL Pattern

Campaigns, CampaignChannels, and UserCommunicationPreferences are Typed models (core entities, referenced directly in C#). CampaignRecipients lists, dashboard cards, and analytics all use DynamicRow via ExecuteDynamicListAsync / ExecuteDynamicPagedListAsync — a direct application of the platform's existing 30% Typed / 70% Dynamic rule, not a new decision.

## 12.3 API Endpoints (Phase 1)

| Method & Path | Purpose |
| --- | --- |
| GET /api/v1/superadmin/communication/dashboard | KPI cards + chart data |
| GET /api/v1/superadmin/campaigns | Paged campaign list (Dynamic, filterable/sortable) |
| POST /api/v1/superadmin/campaigns | Create draft campaign |
| PUT /api/v1/superadmin/campaigns/{id} | Update draft campaign |
| GET /api/v1/superadmin/campaigns/{id} | Full campaign detail (wizard reload / view) |
| POST /api/v1/superadmin/campaigns/{id}/estimate-audience | Cached recipient count for current audience rules |
| POST /api/v1/superadmin/campaigns/{id}/test-send | Send Push/Email to admin or internal testers only |
| POST /api/v1/superadmin/campaigns/{id}/send | Send now (enqueues via Hangfire) |
| POST /api/v1/superadmin/campaigns/{id}/schedule | One-time scheduled send |
| POST /api/v1/superadmin/campaigns/{id}/cancel | Cancel a scheduled/running campaign |
| GET /api/v1/superadmin/campaigns/{id}/history | Delivery/open/click detail for one campaign |
| GET/PUT /api/v1/communication-preferences | Self-service preferences (any authenticated user, not Super Admin only) |
| POST /api/v1/webhooks/ses-events | AWS SES/SNS delivery, bounce, open, click notifications |

# 13. Security & Compliance

- RBAC: Create, Edit, Approve, Send, and Cancel are restricted to the Super Admin role only, per the original spec — enforced via the existing JWT role claim, no new auth mechanism required.

- Full audit trail: every campaign write flows through the platform's existing AuditLogs table (extend EntityName values to include “Campaign”) — captures who, when, IP address, and before/after values automatically.

- Provider API keys (SES, FCM, Fast2SMS) live in the Settings table with IsPublic=0, consistent with existing platform convention — never exposed to any frontend.

- Opt-out enforcement: UserCommunicationPreferences is checked before any promotional send; transactional messages (OTP, password reset, critical account alerts) explicitly bypass these preferences, matching the spec's own stated rule and standard legal practice.

- SMS compliance: no promotional SMS is sent until Fast2SMS DLT registration (TRAI mandate) is complete — enforced by simply not enabling the SMS channel in Phase 1, rather than a runtime check that could be missed.

- Duplicate-send protection and required confirmation-before-send (Phase 1 Step 6) reduce the risk of accidental mass-sends to the full user base.

# 14. Performance & Scalability Architecture

- Queue-based asynchronous processing via Hangfire (Phase 0) — API requests enqueue work and return immediately; sending happens in background workers.

- Batch sending (500–1,000 recipients per batch) to avoid provider rate-limit throttling on SES/FCM/SMS gateways.

- Configurable exponential backoff retry for failed sends, tracked per-batch in CampaignQueueJobs.

- Provider response/message IDs (ProviderMessageId) stored per recipient for delivery reconciliation and support troubleshooting.

- Cached audience-count estimation (Section 11/12.1) avoids expensive live joins at millions-of-users scale.

- This aligns directly with the platform's existing Scale Roadmap: current single-instance MySQL setup is adequate through Phase 3; extracting to Azure Service Bus / dedicated workers is already the documented plan at the 200k–1M user tier, not a new decision introduced by this module.

# 15. Risks & Blind Spots

- Hangfire is new to this codebase — budget time for it in Phase 0 even though it's “just” infrastructure; a shaky job engine undermines every phase built on top of it.

- SMS re-enablement depends entirely on an external party (the DLT/telecom registration process) — track its lead time separately from the dev schedule so it doesn't silently become the critical path.

- Sending to “millions” of real users is a reputational risk as much as a technical one — SES and FCM both penalize senders with high bounce/complaint rates. Recommend Phase 1 goes live to a capped, monitored audience size first, then ramps up once delivery/complaint metrics are proven healthy.

- The Notifications table (existing, per-user transactional notices) and the new CampaignRecipients table (bulk campaign tracking) will look similar but serve different purposes — worth a short naming/documentation pass so future developers don't conflate or merge them incorrectly.

- A/B testing, approval workflows, and the Message Queue console (Phase 3) are genuinely complex even at large companies — treat the Phase 3 estimate as a floor, not a ceiling, until Phase 1 delivery experience informs it better.

# 16. Effort Estimate & Resourcing

| Phase | Developer-Weeks | Parallel/External Dependencies |
| --- | --- | --- |
| Phase 0 — Foundation | 1.5–2 | None — can start immediately |
| Phase 1 — MVP Campaigns | 3–4 | None — SES already production-ready |
| Phase 2 — Targeting/Templates/Recurring | 3 | None |
| Phase 3 — Operational Maturity | 3–4 | None |
| Total (Phase 0–3) | 10–13 | — |
| SMS re-enablement (whenever DLT clears) | 0.5–1 (incremental) | Blocked on external DLT registration — not counted in the total above |

Estimates assume one to two developers working with the existing Controller → Interface → DAL → Stored Procedure pattern already established across the platform; no new architectural pattern needs to be learned.

# 17. Recommended Additions to the Architecture Decisions Log

| # | Decision | Rationale |
| --- | --- | --- |
| 22 | Communication Center delivered in 4 phases (Foundation / MVP / Targeting+Templates / Ops Maturity), Phase 4 items tracked as confirmed future scope | Full original spec as one release was assessed as too high-risk/onerous for a single delivery |
| 23 | Hangfire adopted for background job processing | No async job engine previously existed; required foundation for scheduling, queueing, retries across the whole module |
| 24 | SMS channel excluded from Phase 1; Push + Email only until Fast2SMS DLT registration completes | TRAI mandate — Fast2SMS “Quick” route cannot legally carry real promotional SMS |
| 25 (correction) | SMS provider is Fast2SMS, not Twilio/MSG91 as previously documented | Codebase inspection found the real implementation differs from the earlier stack decision |
| 26 (correction) | Cloud is AWS-only in practice (S3 + SES), not “Azure primary” as previously documented | Codebase inspection found no Azure services in current use |

These will be written into the software-architect-skill's Decisions Log once this plan is approved, per the skill's own Self-Update Protocol.

# 18. Appendix — Full Feature Traceability

Every item from the original feature request, mapped to the phase that delivers it, so nothing from the original ask is silently dropped.

| Original Request Item | Delivered In |
| --- | --- |
| Push / Email / SMS sending | Phase 1 (Push+Email); SMS on DLT clearance |
| Dashboard KPI cards & charts | Phase 1 (core cards), Phase 2 (full chart set) |
| Create Campaign wizard (Steps 1,2,4,6) | Phase 1 |
| Audience: All/Active/Inactive/New/By Org/By Role | Phase 1 |
| Audience: Location/Gender/Age/Language/Interest/CSV/Manual search | Phase 2 |
| Scheduling: Send Now / one-time Schedule | Phase 1 |
| Scheduling: Recurring / Custom Cron | Phase 2 |
| Campaign Templates | Phase 2 |
| Campaign History table + Actions | Phase 1 (core), Phase 2 (Export) |
| Per-campaign detailed analytics & charts | Phase 1 (core), Phase 2 (timelines/heatmap) |
| Audience Segment Builder (save/reuse) | Phase 2 |
| Message Queue console + controls | Phase 3 |
| Provider Settings (Firebase/SES/Fast2SMS config) | Phase 0 (Settings entries), UI in Phase 3 |
| User Communication Preferences | Phase 0 (schema + enforcement), Phase 1 (self-service UI) |
| A/B Testing | Phase 3 |
| Personalization variables | Phase 1 |
| Duplicate Protection | Phase 3 |
| Test Send | Phase 1 |
| Draft Auto Save | Phase 3 |
| Campaign Clone | Phase 3 |
| Maker-Checker Approval Workflow | Phase 3 |
| Security/Audit Log | Phase 1 onward (data capture), Phase 3 (review UI) |
| WhatsApp, in-app inbox, web push, drip automation, AI copy, geo-fencing, budgeting, CRM integration | Phase 4 — confirmed future scope |

End of document.